## Sheet1
Risk | Outcome | Responsibility | Impact | Likelihood | Risk factor | Control/mitigation | Response | Impact | Likelihood | risk factor
Database at risk of being hacked/SQL injection | Loss of data or stolen data | Developers | 5 | 3 | 15 | Strong DB password, encrypt traffic so details cannont be intercepted, use third party security like stripe | prevent users from inputing any new information into the database untill the issue is resolved, fix breach, inform relevent authorities | 4 | 2 | 8
Database servers could be overloaded with requests | Database server could become unstable or even out of commision | Developers | 3 | 3 | 9 | Database could be moved onto a cloud based server where it can be monitored and if more load is needed the cloud database can be adjusted to match | if the server gets overloaded then it will be migrated over to a cloud based database. Current databse will be monitored | 3 | 1 | 3
Unforseen errors or bugs to occur in the application | Connection to database to break, information not being stored correctly | Developers | 3 | 4 | 12 | High coverage of tests to ensure the code works as it should. quick bug fixes, isolate the bugs so the rest of the application can still work | If we come across bugs, we should aim to resovle them as fast as posible while being thorough to ensure the same bug doesnt occur again | 2 | 3 | 6
Risk Assessment by: | Sean Palla |  | Date | 26/07/2022